## Sheet1
Semester A
No of Task | Task Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Setting up aims and finding details of phage , CNN and DNA in this project | bar: 1 to 2
2 | Background study and Using PubMed to search relative findings and research | bar: 2 to 3
3 | Collecting phage protein data and finish data pre-processing | bar: 3 to 6
4 | Generating data set for training model and Try different model and compare their performance | bar: 7 to 10
5 | Progress Report Submission | bar: 11 to 12
Semester B
6 | Fine tune model and try to get better performance | bar: 1 to 3
7 | Record the result of the model and use result to do data visualization | bar: 3 to 4
8 | Making project conclusion and reviewing the model | bar: 5 to 6
9 | Prepare presentation and use the model to demo it performance | bar: 7 to 8
10 | Final report writing | bar: 9 to 12